## GuestDoor_Test_Cases
Name of Application |  | Guest Door
Url |  | https://guestdoor-staging.herokuapp.com/
Tester |  | JP Bhatt
Created on Date |  | 2013-04-12
Reviewed on Date
Test Name | Test Description | Step Name | Step Description | Expected Outcome | Actual Outcome | Browser | Status | Github_Defect_ID
GD_Home_Screen_001 | Verifying the sign up link and GUI of sign up page | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | Sign up page should be opened with the following details: First Name, Last Name, Email Address, Password , Confirm Password and a button of "List your home for free" should be there At the footer of the page following links should appear: Home, Contact, About, Legal, Blogs and Articles. | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on Sign up link |  |  |  | Pass
GD_Home_Screen_002 | Verifying About GuestDoor link and UI of coming page | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | A page should open with the details about GuestDoor and one "Sign Up" link should be available | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "About GuestDoor" link
GD_Home_Screen_003 | Verifying Sign in link and UI of sign in page | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | Sign in page should be opened with two fields as: Email address and password, user picture should also get display And two links: Sign up and Forgot your password should be present | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on sign in link
GD_Home_Screen_004 | Verifying the "Contact" link | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | Contact page should get opened with the following details: How can we help you?, Additional details, Name, Your email address, Phone number. A submit button should be there On the same page two options : Email support and twitter should be present | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "Contact" link
GD_Home_Screen_005 | Verifying the "Legal" link | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | User should be redirected to the legal page | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "Legal" link
GD_Home_Screen_006 | Verifying the "Legal" link | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | User should be redirected to the "Blog and Articles" page | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "Blog and Articles" link
GD_Home_Screen_007 | Verifying the Search box availability on the home screen | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | There should be search box on the home screen with the 3 options: check in date, check out date and number of guest box |  | Chrome 25 | Pass
GD_Sign_Up_008 | Verifying valid advertisement | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com" in the browser | Passed date advertisement should not get displayed | Passed date advertisement is getting displayed | Chrome 25 | Fail | #13
|  | Step 2 | Click on the sign up link
GD_Sign_Up_009 | Closing the sign up page | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com" in the browser | A close option should be there | There is no way to close the sign up page | Chrome 25 | Fail | #14
|  | Step 2 | Click on the sign up link
GD_Sign_Up_010 | Creation of an account | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | After entering all the required fields a user account should get created and user should be redirected to the home page of the application | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on Sign up link
|  | Step 3 | Enter all the mandatory fields
|  | Step 4 | Press Enter
GD_Sign_Up_011 | Welcome mail after sign up | Step 1 | Pre-requisite : A new account should be created | A welcome email should come to the newly registered user | No email comes to the registered mail id | Chrome 25 | Fail | #15
GD_Sign_Up_012 | Availability of sign up button | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com" in the browser | A sign up button should be available | There is no button available to sign up on the sign up page, once needs to press enter | Chrome 25 | Fail | #16
|  | Step 2 | Click on the sign up link
GD_Sign_In_Page_013 | Verifying the UI "Sign In" page | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | A page should open with the text boxes as "Email Address" and "Password" and Profile picture icon Sign up and forgot password link should also appear | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on sign in link
GD_Sign_In_Page_014 | Verifying the picture fields of "Sign In" page | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | A message should appear to enter the credentials or something related to sign in | No message displays and user gets redirected to the home page of the application | Chrome 25 | Fail | #17
|  | Step 2 | Click on sign in link
|  | Step 3 | Without entering the valid credentials Click on the profile pic icon
GD_Sign_In_Page_015 | Verifying the UI of home page after signing in/first time sign up | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | A page should open with the link like "My Stays" at the top right corner And user name should appear with the drop down icon with the following options : Dashboard, My Listings, Profile, Favorites, Billing, Sign out | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on sign in link
|  | Step 3 | Enter the credentials
|  | Step 4 | Press Enter
GD_Sign_In_Page_016 | "Sign in" functionality | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | A sign in button should be available | There is no button available to sign in on the sign in page, one needs to press enter | Chrome 25 | Fail | #18
|  | Step 2 | Click on the sign in link
GD_Search_017 | Search button functionality | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | Message related to the particular error should appear | Error message is not related to error | Chrome 25 | Fail | #19
|  | Step 2 | click on search without entering any data
GD_Search_018 | Verifying number of guest button functionality | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | Message related to the particular error should appear like: no such home available as per your requirement | Error message is not related to error | Chrome 25 | Fail | #20
|  | Step 2 | Enter 9 in the guest text box
|  | Step 3 | click on search
GD_My_Stays_019 | Verifying the UI of "My stays" page | Step 1 | Pre-requisite : User is already logged in and at home page | "MY Stays" page should get opened with the following options : Dashboard, My Listings, My Stays Favorites, Profile, Billing And confirmed stay list should get displayed | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "My Stays" present at the top right corner of the screen
GD_Dashboard_020 | Verifying the UI of dashboard screen | Step 1 | Pre-requisite : User is already logged in and at home page | User should be redirected to the "Dashboard" screen with the information like: My Listings, My info. My listing should include all user listing and for the first time there should be a link to add listing My info should include the: Listings, Booking , Stays. And a option to edit the profile | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "My Stays" present at the top right corner of the screen
|  | Step 3 | Click on "Dashboard" from the list available at the left side of the screen
GD_Edit_Profile_021 | Verifying the UI of edit profile screen under Dashboard | Step 1 | Pre-requisite : User is already logged in and at home page | User should be redirected to "Edit my profile" page with the following options: First Name, Last Name, Email , Location and a option on R.H.S to add picture And a option to change password should also be there which includes two boxes as : New Password, Password Confirmation , two buttons : update and back should be there | As Expected | Chrome 25 | Pass
|  | Step 2 | Click on "My Stays" present at the top right corner of the screen
|  | Step 3 | Click on "Dashboard" from the list available at the left side of the screen
|  | Step 4 | Click on "Edit my profile"
GD_Edit_Profile_022 | Verifying the functionality of "Edit Profile" | Step 1 | Pre-requisite : User is already logged in and at home page | Except location should be empty and rest fields should be filled | Location field contains the email id | Chrome 25 | Fail | #21
|  | Step 2 | Click on "My Stays" present at the top right corner of the screen
|  | Step 3 | Click on "Dashboard" from the list available at the left side of the screen
|  | Step 4 | Click on "Edit my profile"
GD_Edit_Profile_023 | Verifying the functionality of "Edit Profile" | Step 1 | Pre-requisite : User is already logged in and at home page | An Error message should come on the same screen with proper layout | Layout is not proper | Chrome 25 | Fail | #22
|  | Step 2 | Click on "My Stays" present at the top right corner of the screen
|  | Step 3 | Click on "Dashboard" from the list available at the left side of the screen
|  | Step 4 | Click on "Edit my profile"
|  | Step 5 | Enter all the fields except "last name"
|  | Step 6 | click on update button
GD_ListYourHome_024 | Verifying the functionality of About the Space section of "List you Home". | Step1 | Pre-requisite: User is already logged in and clicks on List Your Home. | About the space details should be saved and Photos and Videos section should be opened | Address is mentioned instead of Address1. | Chrome25 | Pass
|  | Step2 | Fill in Location details.(Address ,Address 2,Country, State/Territory, City, ,Postal Code, Rental type)
|  | Step3 | Fill in How your listing will appear section.
|  | Step4 | Fill in Features & Amenities
|  | Step5 | Fill in House Rules
|  | Step6 | Click on NEXT Photo and Video
GD_ListYourHome_025 | Verifying the functionality of Photos and Video Section. | Step1 | Pre-requisite: User is already logged in and clicks on List Your Home. | Photo should be uploaded successfully and displayed. | Photo is uploaded and displayed successfully. | Chrome25 | Pass
|  | Step2 | Click on Upload photo and select browse image
|  | Step3 | Image should be uploaded and displayed successfully.
GD_ListYourHome_026 | Verifying the functionality of Photos and Video section. | Step 1 | Pre-requisite: User is already logged in and clicks on List Your Home. | Pop Up message should be displayed. | Pop Up message is displayed that File must be an image | Chrome25 | Pass
|  | Step 2 | Click on Upload photo and select csv file or any other extension other that jpg.
GD_ListYourHome_027 | Verifying the functionality of Photos and Video section. | Step 1 | Pre-requisite: User is already logged in and clicks on List Your Home. | Video link should not be saved and validation message should be displayed. | Video link gets saved without any validation message. | Chrome25 | Fail | #23
|  | Step 2 | Upload an image and provide only text in Video URL and click on update Listing.
GD_ListYourHome_028 | Verifying the functionality of Photos and Video section. | Step 1 | Pre-requisite: User is already logged in and clicks on List Your Home. | Video should be displayed in Video tab. | Video is displayed in video tab. | Chrome25 | Pass
|  | Step 2 | Provide Valid Video URL of house description.
GD_List_YourHome_029 | Verifying the functionality of Bookings section. | Step 1 | Pre-requisite: User is already logged in and clicks on List Your Home. | Booking details should get saved successfully. | Booking details are getting saved successfully. | Chrome25 | Pass
|  | Step 2 | Select Allow offers as yes and allow swaps as yes in Booking and Offers section.
|  | Step 3 | Select " This listing is public" Who can see this listing
|  | Step 4 | Fill and save all required fields.
GD_List_Your_Home_030 | Verifying the functionality of "List your home" option | Step 1 | Pre-requisite: User is already logged in | User should be able to list his/her home | "Next photo and video" button is disabled | IE8, 9, 10 | Fail | #24
|  | Step 2 | Click on "List your home" present at the top right corner of the screen
GD_List_Your_Home_031 | House rules functionality | Step 1 | Pre-requisite: User is already logged in | All the buttons/ texts should be properly aligned | House rules box layout is not fine | Firefox 19 | Fail | #25
|  | Step 2 | Click on "List your home" present at the top right corner of the screen
GD_List_Your_Home_032 | Sign in using IE 10 | Step 1 | Enter the URL: "https://guestdoor-staging.herokuapp.com/" | Text should fully visible | Text is not fully visible | IE 10 | Fail | #26
|  | Step 2 | Click on sign in link
GD_EditProfile_033 | Add Photo in IE8 | Step 1 | Pre-requisite: User is already logged in | Browse button should be in proper size . | Browse button is not getting displayed in proper size. | IE8, 9, 10 | Fail | #27
|  | Step 2 | Go to Edit Profile.
|  | Step 3 | Click Add Photo and verify the Browse button size.
GD_Edit_Profile_034 | Photo link is not clickable. | Step1 | Pre-requisite: User is already logged in | Hyperlink for Photo should be clickable. | Hyperlink for Photo is not clickable. | IE8+,FireFox19,Chrome 25 | Fail | #28
|  | Step2 | Go to Edit Profile.
|  | Step3 | Click on Photo hyperlink.
GD_Cross_Site_035 | Checking the application for cross site scripting vulnerability | Step1 | Enter the URL: "https://guestdoor-staging.herokuapp.com" in the browser | Application should not accept the source code of any other site and relevant error message should appear to the user. | Application accepts the source code of other site | Firefox 19/ Chrome | Fail | #29
|  | Step2 | Click on "Contact" link
|  | Step3 | In all the mandatory fields expect email address, enter the source code of any other site
GD_SQL_Injection_036 | Checking the application for SQL injection | Step1 | Enter the URL: "https://guestdoor-staging.herokuapp.com" in the browser | Application should not accept the SQL queries. | Application accepts the SQL queries and relevant error message should appear to the user. | Firefox 19/ Chrome | Fail | #30
|  | Step2 | Click on "Contact" link
|  | Step3 | In all the mandatory fields expect email address, enter any SQL query
GD_List_Your_Home_037 | Checking the application for the maximum no. of images we can upload for one particular listed home | Step1 | Pre-requisite: User is already logged in | Either an option should be there to add more images or maximum limit should appear | Neither add more images option nor max limit reached message appears | Firefox 19/ Chrome | Fail | #31
|  | Step2 | Click on "List your home" present at the top right corner of the screen
|  | Step3 | Fill the mandatory fields of the first page "About the space" and move to "Photos and videos"
|  | Step4 | upload 20 images
GD_List_Your_Home_038 | Checkout time is not updated when we manually type the check out time instead of selecting by arrow. | Step 1 | Pre-requisite: User is already logged in | Checkout time should be updated if we enter it manually. | Checkout time is not updated but it is displayed as check in Time. | IE8+,FireFox19,Chrome 25 | Fail | #32
|  | Step 2 | Click on List Your Home
|  | Step 3 | Fill Check In and Checkout time manually instead of selecting by arrows.
GD_List_Your_Home_039 | Wrong page is displayed after we press back navigation twice on error page of payment method. | Step 1 | Pre-requisite: User is already logged in | Back navigation should displayed the page of listings and booking modules. | Wrong page is displayed after we press back navigation twice on error page of payment method. | IE8+,FireFox19,Chrome 25 | Fail | #33
|  | Step 2 | Click on List Your Home and then go to Add Payment method in billing module..
|  | Step 3 | Click on Add Payment Method with blank values. Error is displayed then click on back button .
|  | Step 4 | Click on back button again.
GD_List_Your_Home_040 | All Labels are hyperlinks in Booking page in List Your Home. | Step 1 | Pre-requisite: User is already logged in | Labels should not be mentioned as hyperlink in Booking page. | Labels are hyperlinks in booking page. | IE8+,FireFox19,Chrome 25 | Fail | #34
|  | Step 2 | Click on List Your Home.
|  | Step 3 | Go to Booking Page.
GD_List_Your_Home_041 | Image Resolution is not displayed properly after we upload small image of size 22*22 in add photo of List You Home. | Step 1 | Pre-requisite: User is already logged in | Image should be visible properly. | Image is not visible properly. | IE8+,FireFox19,Chrome 25 | Fail | #35
|  | Step 2 | Click on List Your Home.
|  | Step 3 | Go to Photos and Video section.
|  | Step 4 | Upload am image of small size(22*22) and verify it on Photos section of advertisement.
GD_List_Your_Home_042 | Alignment is not proper when we upload image of large name in Photos section of List Your Home | Step 1 | Pre-requisite: User is already logged in | Image name should be displayed with in pop up | Image name is displayed outside pop up. | IE8+,FireFox19,Chrome 25 | Fail | #36
|  | Step 2 | Go to List Your Home.
|  | Step 3 | Go to Photos and Video section and upload am image of large name.
GD_List_Your_Home_043 | Video is not displayed after we click on Update Listing in Photos and Video section but it displayed after we click on Map and then click Video section. | Step 1 | Pre-requisite: User is already logged in | Video should be displayed in video section. | Video is not displayed after we click on Update Listing in Photos and Video section but it displayed after we click on Map and then click Video section. | IE8+,FireFox19,Chrome 25 | Fail | #37
|  | Step 2 | Go to List Your Home and click Photos and Video section.
|  | Step 3 | Click on Update listing after uploading Video.
GD_List_Your_Home_044 | To verify the delete functionality of the uploaded images | Step 1 | Pre-requisite: User is already logged in and listed a home with images | A confirmation message window should appear | No confirmation message appears | Firefox 19/ Chrome 25 | Fail | #38
|  | Step 2 | Select the listed home and click on edit
|  | Step 3 | Select photos and videos tab
|  | Step 4 | Click on cross icon at the top right corner of the image in order to delete it
GD_List_Your_Home_045 | To check the deletion and deactivation property of the listed home | Step 1 | Pre-requisite: User is already logged in and listed a home with images | An option should be there to deactivate or delete the listed home | Except editing no option related to deactivation/deletion is available | Firefox 19/ Chrome 25 | Fail | #39
|  | Step 2 | Select the listed home
GD_Street_View_046 | To check the street view the listed home | Step 1 | Pre-requisite: User is already logged in and listed a home with required data | Complete view of the listed home should appear to the user (the home picture as well as street no) | Partial view is available as only the street no appears to the user but not home picture | Firefox 19/ Chrome 25 | Fail | #40
|  | Step 2 | Select the listed home
Select the "Street View" option
GD_Swap__047 | To check the swap functionality | Step 1 | Pre-requisite: User is already logged in and listed a home with required data | Expiration date should accept the US date format and Default format should be mentioned for the ease. | Expiration date does not accept the US date format | Firefox 19/ Chrome 25 | Fail | #41
|  | Step 2 | Select any other home (e.g.: Guesthouse in the country Entire Home • 123 N 4th Street, Apt 5, Corn, Oklahoma, US) for which you wants to check the swap functionality
|  | Step 3 | If swap functionality available click on "Swap Places" link
|  | Step 4 | While filling the form enter the date in the "Expiration Date" field with the same format as provided in check in/out field.
GD_List_Your_Home_048 | Selection of dates to rent the home | Step 1 | Pre-requisite: User is already logged in and listed a home with required data | An option should be there to list the home for rent as per the time period decided by the owner | No such option is available where user can rent his/her home for a given time period | Firefox 19/ Chrome 25 | Fail | #42
|  | Step 2 | Select the "List your home" option
|  | Step 3 | Fill all the mandatory field in the "About the space" tab
|  | Step 4 | Upload images and videos under "photos and videos" tab
|  | Step 5 | Fill all the mandatory field in the "Booking" tab
|  | Step 6 | Fill all the special rates and blackout dates in the "Availability and Rates" tab
GD_List_Your_Home_049 | To check the functionality of "View other listings close by" link in Listing page. | Step 1 | Pre-requisite: User is already logged in | Other listings in the nearby locations should be displayed. | Error page related to "Something went wrong " displays. | IE8+,FireFox19,Chrome 25 | Fail | #43
|  | Step 2 | Go to My Listing and open any listing.
|  | Step 3 | Click on Go to other listings close by
GD_List_Your_Home_050 | To check "Update button" functionality | Step 1 | Pre-requisite: User is already logged in | Favorite list should be updated once we click on "update favorite" button. | Update Favorite button does not work. | IE8+,FireFox19,Chrome 25 | Fail | #44
|  | Step 2 | Go to Favorites section.
|  | Step 3 | Click on update favorite.
GD_List_Your_Home_051 | To check the functionality od "Change Password" option in the edit | Step 1 | Pre-requisite: User is already logged in | Validation message should be displayed when we provide blank password in the "Change password" field of edit profile page. And account updated successfully message should not get displayed | Instead of throwing error message when one enters blank values in the "change password" field, application throws account updated successfully message to the user | IE8+,FireFox19,Chrome 25 | Fail | #45
|  | Step 2 | Go to Edit Profile and provide blank space in password and confirm password field.
GD_List_Your_Home_052 | Layout is not proper when we provide blank value in First and Last Name of Edit Profile page. | Step 1 | Pre-requisite: User is already logged in | Layout should be proper | Layout is not proper | IE8+,FireFox19,Chrome 25 | Fail | #46
|  | Step 2 | Go to Edit Profile and provide blank values in First and Last Name and save it.
GD_List_Your_Home_053 | Alignment is not proper at 90% zoom of Listing Home section. | Step 1 | Pre-requisite: User is already logged in | Alignment should be displayed properly. | Alignment does not display properly. | IE8+,FireFox19,Chrome 25 | Fail | #47
|  | Step 2 | Verify the listing page as 90% Zoom.
GD_List_Your_Home_054 | Functionality of profile picture | Step 1 | Pre-requisite: User is already logged in and listed a home | Layout should be proper | Layout is not proper | Firefox/ Chrome | Fail | #48
|  | Step 2 | Click on "My bookings"
|  | Step 3 | Click on "Dashboard" from the list available at the left side of the screen
|  | Step 4 | Click on the profile picture
GD_List_Your_Home_055 | Functionality of "Create offer" page | Step 1 | Pre-requisite: User is already logged in and listed a home | Data entered by the user and button name should not get changed as after clicking create offer button control redirects to the same page | Data in the "rate per night" field and "create offer" button text get changed once we click on "create offer" button | Firefox/ Chrome | Fail | #49
|  | Step 2 | Select any other home for which you wants to check the create offer functionality
|  | Step 3 | Click on "Create Offer" link
|  | Step 4 | Enter 150 or any amount in the "rate per night" field
|  | Step 5 | Click on "Create offer" button
GD_List_Your_Home_056 | Checking all the fields of "About the space" tab | Step 1 | Pre-requisite: User is already logged in | Negative number should not get accepted or a validation message should be there | "sleeps up to" field accepts negative number | Firefox/ Chrome | Fail | #50
|  | Step 2 | Click on the "List your home" link
|  | Step 3 | Enter any negative number in the "sleeps up to" field
|  | Step 4 | Fill all the mandatory fields and save it
GD_List_Your_Home_057 | Loading heavy images in the home | Step 1 | Pre-requisite: User is already logged in | As the application accepts heavy images without any warning message so it should get opened too | If one try to open a listed home of heavy images then an error message appears to the screen | Firefox/ Chrome | Fail | #51
|  | Step 2 | Click on the "List your home" link
|  | Step 3 | Fill all the mandatory fields in the "About the space" tab and click on "next photos and videos" tab
|  | Step 4 | Upload heavy images in the "Photos and videos" tab
|  | Step 5 | Click on update listing
GD_List_Your_Home_058 | Add a listed home to favorites | Step 1 | Pre-requisite: User is already logged in | There should be an error message indicating that the mandatory field cannot be empty | Accepting blank value in the mandatory field | Firefox/ Chrome | Fail | #52
|  | Step 2 | select any listed home which you want to add to fav.
|  | Step 3 | Click on fav. Icon
|  | Step 4 | Leave the "List Name" field blank
|  | Step 5 | Click on create fav. Item button
GD_List_Your_Home_059 | Make an Offer for a Listing and provide negative value in "Rate per Night" field | Step1 | PreRequisite: Listing is displayed in search results. | Validation message should be displayed that "Rate per Night" is invalid. | Validation message is displayed that "Rate per Night" is invalid. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer"
|  | Step3 | Provide negative value in Rate Per Night field.
|  | Step4 | Click on Create Booking.
GD_MakeAn Offer_060 | Make An Offer for a Listing and provide a value less than 4 in "Rate per Night" field. | Step1 | PreRequisite: Listing is displayed in search results. | Validation message should be displayed that "Must be greater than 4." | Validation message is displayed that "Must be greater than 4." | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer"
|  | Step3 | Provide 0 in Rate per night field.
GD_MakeAn Offer_061 | Make An Offer for a listing and CheckIn and CheckOut Date same. | Step1 | PreRequisite: Listing is displayed in search results. | Booking should get created successfully. | Error message is displayed but error message is not explanatory. | Firefox/ Chrome | Fail | #54
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer"
|  | Step3 | Select same date in CheckIn and CheckOut Date.
GD_MakeAn Offer_062 | Make An Offer for an already booked listing and Provide overlaping date. | Step1 | PreRequisite: Listing is displayed in search results. | Validtion message should be displayed that "Listing is not available for specified date range" | Validtion message is displayed that "Listing is not available for specified date range" | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step 3 | Provide similare date range of already booked listing.
GD_MakeAn Offer_063 | Make An Offer for a listing and Create booking. | Step1 | PreRequisite: Listing is displayed in search results. | Booking should get created successfully under My Stays of Guest Login and under My Booking tab for Host Login. | Booking is created successfully under My Stays of Guest Login and under My Booking tab for Host Login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
GD_MakeAnOffer_064 | Make An Offer from Guest Login and Decline Offer from Host Login. | Step1 | PreRequisite: Listing is displayed in search results. | Booking should be cancelled and for Host Login it should be displayed under Closed bookings and for Guest Login it should be displayed under Closed Stays | Booking is cancelled and for Host Login it displays under Closed bookings and for Guest Login it displays under Closed Stays | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step 4 | Login with Host Login "Owner of booked listing"
|  | Step 5 | In My Booking Section go to Pending Booking listings.
|  | Step 6 | Go to "Decline" section and after filling message click on Decline Offer button.
GD_MakeAnOffer_065 | Make An Offer from Guest Login and Cancel Offer from Guest login. | Step1 | PreRequisite: Listing is displayed after search. | Booking should be cancelled and displayed under "Closed Stays" section for Guest Login and "Closed Bookings" section of Host Login. | Booking is cancelled and displayed under "Closed Stays" section for Guest Login and "Closed Bookings" section of Host Login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step 4 | Click on "Need to cancel" hyperlink and Click on Cancel Offer after filling message field
GD_MakeAnOffer_066 | Make An Offer from Guest Login and Accept Offer from Host Login. | Step1 | PreRequisite: Listing is displayed after search. | Listing should be booked and displayed under Confirmed Stays for Guest login and Confirmed Bookings for Host Login. | Listing is booked and displayed under Confirmed Stays for Guest login and Confirmed Bookings for Host Login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Login with Host login and click on accept offer.
GD_MakeAnOffer_067 | Make An Offer from Guest Login and Provide negative value in "Rate per Night" for Counter offer from Host Login. | Step1 | PreRequisite: Listing is displayed after search. | Error message should be displayed for Rate per night field. | Error message is displayed but Message box is displayed twice and "Create Booking" button is displayed instead of "Counter Offer" | Firefox/ Chrome | Fail | #55
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Login with Host Login and provide negative value in "Rate per Night" and Click on Counter Offer.
GD_MakeAnOffer_068 | Make An Offer from Guest Login and Counter offer from Host Login. | Step1 | PreRequisite: Listing is displayed after search. | Counter offer should be submitted and displayed to Guest login. | Counter offer is submitted and displayed to Guest login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Login with Host Login and provide a value less that Rate per night offered and click on counter offer.
GD_MakeAnOffer_069 | Make An Offer from Guest Login and Counter offer from Guest Login. | Step1 | PreRequisite: Listing is displayed after search. | Counter offer should be submitted and displayed in Host Login. | Counter offer is submitted and displayed in Host Login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Login with Host and click on Counter Offer after filling "Rate per Night" and change "CheckOut" date.
GD_AcceptAnOffer_070 | Make An Offer from Guest Login and Accept Offer from Host Login. | Step1 | PreRequisite: Listing is displayed after search. | Offer should be accepeted and listing should be displayed under My Stays for Guest Login and under My Bookings for Host Login. | Offer is accepeted and listing is displayed under My Stays for Guest Login and under My Bookings for Host Login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Login with Host Login and click on accept offer .
GD_DeleteAnOffer_071 | Make an Offer from Guest Login and then delete the booking. | Step1 | PreRequisite: Listing is displayed after search. | Booking should be cancelled . | Booking is cancelled but page is getting redirected to Home Page. | Firefox/ Chrome | Fail
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Click on cross for cancelling the booking.
GD_MakeAnOffer_072 | Make an Offer and then do not respond till 23 hours and verify the status of an offer. | Step1 | PreRequisite: Listing is displayed after search.
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling all values.
|  | Step4 | Do not respond till 23 hours after making an offer and then verify the status of Booking from Guest and Host Login.
GD_MakeAnOffer_>1_Guest_073 | Make and Offer from Guest Login and provide value more than 1 in Guest field. | Step1 | PreRequisite: Listing is displayed after search. | Validtion message should be displayed "Maximum number of guests for listing is 1" | Maximum word is displayed as "Maximumn" after error message is displayed. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Click on Create Booking after filling 2 in Guests field.
GD_MakeAnOffer_074 | Make an Offer from Guest Login and then verify the My Stays section at 90% zoom. | Step1 | PreRequisite: Listing is displayed after search. | Alignment should be proper when view the My Stay section at 90% zoom. | Alignment is not proper when view the My Stay section at 90% zoom. | Firefox/ Chrome | Fail | #59
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Create Offer after filling in all values.
|  | Step 4 | Verify the alignment at 90% zoom.
GD_MakeAnOffer_075 | Make an Offer from Guest Login and create new Payment method. | Step1 | PreRequisite: Listing is displayed after search. | Offer should be created and listing should be displayed under My Stays for Guest Login and under My Bookings for Host Login. | Offer is created and listing is displayed under My Stays for Guest Login and under My Bookings for Host Login. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Select "New Payment Method" in Pay with dropdow.
|  | Step4 | Click on Create Offer after filling all values along with payment details.
GD_MakeAnOffer_076 | Make an Offer from Guest Login and create new Payment method and provide invalid values in all fields | Step1 | PreRequisite: Listing is displayed after search. | Validation message should be displayed for all fields. | Validation message is not displayed for Postal code and it is accepting character value. | Firefox/ Chrome | Pass
|  | Step2 | Click on Hyperlink for listing and then click on "Make an Offer".
|  | Step3 | Select "New Payment Method" in Pay with dropdow.
|  | Step4 | Provide invalid values for all values of Payment method and click on Create Offer.
GD_BookNow_077 | Book a listing and Create Booking. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be booked and displayed under Pending section of My stays for guest login and Pending bookings section of Host login. | Listing is booked and displayed under Pending section of My stays for guest login and Pending bookings section of Host login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Provide CheckIn,CheckOut date and click on Create Booking.
GD_Accept_PendingOffer_078 | Book a listing and accept pending offer from Host Login. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be displayed under confirmed booking section from Host login and confirmed stays under Guest Login. | Listing is displayed under confirmed booking section from Host login and confirmed stays under Guest Login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Login with Host login and click on accept offer.
GD_Decline_PendingOffer_079 | Book a listing and decline pending offer from Host Login. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be displayed under closed booking section from Host login and closed stays under Guest Login. | Listing is displayed under closed booking section from Host login and closed stays under Guest Login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Login from host and click on decline offer.
GD_CounterOffer_PendingOffer_080 | Book a listing and counter Offer of pending offer from Host Login. | Step 1 | PreRequisite: Listing is displayed after search. | Counter offer details should be displayed in Guest login and Host login. | Counter offer details are displayed in Guest login and Host login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Login from Host Login and then click on counter offer after providing Rate per Night value.
GD_CounterOffer_PendingOffer_081 | Book a listing and accept offer after 1 counter offer from Guest Login. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be displayed under confirmed booking section from Host login and confirmed stays under Guest Login. | Listing is displayed under confirmed booking section from Host login and confirmed stays under Guest Login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Login from Host Login and then click on counter offer after providing Rate per Night value.
|  | Step 4 | Login from Guest and accept offer for the counter offer made from Host.
GD_CancelOffer_Guest_Login082 | Book a listing and cancel offer from guest login. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be displayed under closed stays for guest login and closed booking for host login. | Listing is displaed under closed stays for guest login and closed booking for host login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Login from guest and cancel offer.
GD_DeleteBooking_Guest_Login_083 | Book a listing then delete the booking. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be displayed under closed stays for guest login and closed booking for host login. | Listing is displaed under closed stays for guest login and closed booking for host login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Delete the offer and then verify the status in Guest and Host login.
GD_NewPaymentMethod_BookNow_084 | Book a listing and Select Create payment method while booking. | Step 1 | PreRequisite: Listing is displayed after search. | Listing should be displayed under confirmed booking section from Host login and confirmed stays under Guest Login. | Listing is displayed under confirmed booking section from Host login and confirmed stays under Guest Login. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Listing and click on "Book Now".
|  | Step 3 | Select Create Payment method and click on create booking after filling payment details.
GD_SwapPlaces_NoListing_GuestLogin_085 | Swap places when Guest does not have any listing. | Step 1 | Search any listing | Listings should be displayed under pending swaps of My swaps section. | Listings is displayed under pending swaps of My swaps section. | Firefox/ Chrome | Pass
|  | Step 2 | Click on swap places and create listing as suggested from message.
|  | Step 3 | Now provide CheckIn and CheckOut date and create swap
GD_AcceptOffer_PendingSwaps_HostLogin_086 | Create swap and then accept offer from host login | Step 1 | Search any listing and then create swap. | Swaps should be displayed under confirmed swaps for Guest and Host login. | Swaps are displayed under confirmed swaps for Guest and Host login. | Firefox/ Chrome | Pass
|  | Step 2 | Select accept offer from host login.
GD_DeclineOffer_PendingSwaps_HostLogin_087 | Decline the swap offer from host login. | Step 1 | Search any listing and then create swap. | Listing should be displayed under closed swaps section of My swaps | Listing is displayed under closed swaps section of My swaps | Firefox/ Chrome | Pass
|  | Step 2 | Select Decline offer from host login.
GD_CounterOffer_PendingSwap_088 | Counter offer for pending swap from host login | Step 1 | Search any listing and then create swap. | Message of counter offer should be displayed in guest and host login both and listing should be in pending status. | Message of counter offer is displayed in guest and host login both and listing is in pending status. | Firefox/ Chrome | Pass
|  | Step 2 | Change CheckIn and CheckOut date of host's stays from host login and click on counter offer.
GD_CounterOffer_PendingSwap_089 | Counter offer for pending swap from guest login. | Step 1 | Search any listing and then create swap. | Message of counter offer should be displayed in guest and host login both and listing should be in pending status. | Message of counter offer is displayed in guest and host login both and listing is in pending status. | Firefox/ Chrome | Pass
|  | Step 2 | Login from host and create counter offer for pending swap.
|  | Step 3 | Login from guest and create counter offer from guest login.
GD_CounterOffer_PendingSwap_NegativeScenario_090 | Counter offer for pending swap from guest login. | Step 1 | Search any listing and then create swap. | Error message should be displayed for chekIn and CheckOut date validation. | Error message is displayed but it not explanatory and 3 new message boxes are displayed. | Firefox/ Chrome | Fail | #56
|  | Step 2 | Login from host and create counter offer for pending swap.
|  | Step 3 | Login from guest and create counter offer for pending swap and select CheckIn date greater than CheckOut Date.
GD_CounterOffer_PendingSwap_withSameCheckIn_CheckOutDate_as Previous_091 | Counter offer for pending swap with same checkIn and CheckOut date as previous counter offer swap date. | Step 1 | Search any listing and then create swap. | Counter swap details should be displayed for counter swap from guest login. | Counter swap details are not displayed for counter swap from guest login. | Firefox/ Chrome | Fail | #71
|  | Step 2 | Login from host and create counter offer for pending swap.
|  | Step 3 | Login from guest and create counter swap with same CheckIn and CheckOut date of previous counter swap.
GD_DeleteSwap_092 | Delete a swap from guest login | Step 1 | Search any listing and then create and confirm swap. | Swap should be deleted. | Swap is not getting deleted. | Firefox/ Chrome | Fail | #68
|  | Step 2 | Login from host or guest login and delete the booking in My swaps section.
GD_SwapPlaces_GuestHasMoreThan1Listing_093 | Create swap and guest has 2 listings. | Step 1 | Search any listing and then create swap. | Both the listings should be displayed for swap. | Only 1 listing is displayed for swap. | Firefox/ Chrome | Fail | #69
|  | Step 2 | When user clicks on create swap then verify the listings displayed to swap.
GD_Swap_Places_Guest_Host_TwoSessions_094 | Create a swap from guest login and then verify the my swaps from host login from another browser. | Step 1 | Create a swap from guest login in 1 broswer. | Swap should be created and displayed in my swaps section from host login. | Swap is created and displayed in my swaps section from host login. | Firefox/ Chrome | Pass
|  | Step 2 | Login with host in another browser simultaneously and verify my swaps section
GD_BookNow_Guest_Host_TwoSessions_095 | Create a booking from guest login and then verify the my booking from host login from another browser. | Step 1 | Create a booking from guest login in 1 browser. | Booking should be created and displayed in my bookings section from host login. | Booking is created and displayed in my bookings section from host login. | Firefox/ Chrome | Pass
|  | Step 2 | Login with host in another browser simultaneously and verify my booking section
GD_MakeAnOffer_Guest_Host_TwoSessions_096 | Make an Offer from guest login and then verify the my booking from host login from another browser. | Step 1 | Make An Offer from guest login in 1 browser. | Offer should be displayed in my bookings section from host login. | Offer is displayed in my bookings section from host login. | Firefox/ Chrome | Pass
|  | Step 2 | Login with host in another browser simultaneously and verify my booking section
GD_MakeAnOffer_option_IfOfferNotAllowed_097 | Verify if make an offer is not available for a listing or not. | Step 1 | Create a listing and select the option "No" in allow offers in Booking section. | Make an Offer should not be displayed for the listing. | Make an Offer is not displayed for the listing. | Firefox/ Chrome | Pass
|  | Step 2 | Login with another ID and search the created listing.
|  | Step 3 | Verify the "Make an offer" option for the listing
GD_Swap_option_If_SwapNotAllowed_098 | Verify if swap is available for a listing or not. | Step 1 | Create a listing and select the option "No" in allow swaps in Booking section. | Swap places option should not be displayed for the listing. | Swap places option is not displayed for the listing. | Firefox/ Chrome | Pass
|  | Step 2 | Login with another ID and search the created listing.
|  | Step 3 | Verify the Swap Places option for the listing.
GD_HideListing_098 | Verify if listing is displayed after it is hidden from public. | Step 1 | Login with user and select the option for hiding the listing in Booking section. | Listing should be displayed to public. | Listing is not displayed to public. | Firefox/ Chrome | Pass
|  | Step 2 | Login with another user and verify if listing is displayed
GD_Make Listing_Public_099 | Verify if the listing is displayed after search when it is made public from being hidden. | Step 1 | Login with user and select the option for hiding the listing in Booking section. | Listing should be displayed after search after it is made public from being hidden. | Listing is not displayed after search after it is made public from being hidden. | Firefox/ Chrome | Fail | #73
|  | Step 2 | Login with another user and verify if listing is displayed
|  | Step 3 | Select the option to make the listing to be public.
|  | Step 4 | Login and veirfy if the listing is displayed now.
GD_Allow Swap_Listing_0100 | Verify if the swap option is allowed for a listing after we select "Yes" option from "No" option. | Step 1 | Create a listing and do not allow swap in Booking section. | Swap should be displayed for the listing now. | Swap is displayed for the listing now. | Firefox/ Chrome | Pass
|  | Step 2 | Login with a user Id and verify if the swap option is available for listing.
|  | Step 3 | Go to listing and allow swap option in Booking section.
|  | Step 4 | Verify if the swap option is allowed for that listing now or not.
GD_MakeAnOffer_Available_Listing_101 | Verify if the Make an offer is allowed for a listing after we select "Yes" option from "No" option. | Step 1 | Create a listing and do not allow "Make Offer" in Booking section. | Make an offer should be displayed for the listing now. | Make an offer is displayed for the listing now. | Firefox/ Chrome | Pass
|  | Step 2 | Login with a user Id and verify if the Make an offer is available for listing.
|  | Step 3 | Go to listing and allow "Make Offer "option in Booking section.
|  | Step 4 | Verify if the "Make an offer " option is allowed for that listing now or not.
GD_Create Favorite_102 | Create Favorite list. | Step 1 | Go to Favorite section. | Favorite list should be created successfully. | Favorite list is created successfully. | Firefox/ Chrome | Pass
|  | Step 2 | Provide List Name and select Create Favorite button.
GD_Create Favorite_BlankListName _103 | Create Favorite and provide blank list name | Step 1 | Go to Favorite section. | Validation message should be displayed for blank list name field. | Validation message is displayed for blank list name field. | Firefox/ Chrome | Pass
|  | Step 2 | Provide blank List Name and select Create Favorite button.
GD_CreatePaymentMethod_DifferentSessions_104 | Create Payment method from billing section and open the another session and verify values. | Step 1 | Login and go to billing section. | The values filled in payment method should not be displayed in another session of browser. | The values filled in payment method are not displayed in another session of browser. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Create Payment method
|  | Step 3 | Fill all values and then copy the url.
|  | Step 4 | Paste the url in another session and verify the values filled in form.
GD_CreatePaymentMethod_105 | Create Payment method from billing section. | Step 1 | Login and go to billing section. | Payment method should be created. | Payment method is created. | Firefox/ Chrome | Pass
|  | Step 2 | Click on Create Payment method
|  | Step 3 | Fill all values for payment method.
|  | Step 4 | Click on Create Payment method
GD_DeletePaymentMethod_106 | Delete Payment method created. | Step 1 | Login and go to billing section. | Payment method should be deleted. | Payment method is deleted. | Firefox/ Chrome | Pass
|  | Step 2 | Create Payment method.
|  | Step 3 | Delete the payment method
GD_CreateAnotherPaymentMethod_WhileBooking_107 | Create another payment method while booking. | PreRequisite | User has added 1 payment method already. | Another payment method should be created. | Another payment method is created. | Firefox/ Chrome | Pass
|  | Step 1 | Select Book Now for a listing .
|  | Step 2 | Click on create payment method and book th elisting.
|  | Step 3 | Go to billing section and verify if another payment method has been created.
GD_AddedPaymentMethod_Displayed_WhileBooking_108 | Book the listing and verify if another payment method added in billing section is displayed in dropdown. | Step 1 | Select Book Now for a listing. | All payment methods added should be displayed in dropdown. | All payment methods added are displayed in dropdown. | Firefox/ Chrome | Pass
|  | Step 2 | Verify if all payment method are displayed in dropdown
GD_AddedPaymentMethod_Displayed_WhileBooking_109 | Verify the transaction section after booking. | Step 1 | Search listing and book this listing. | All transactions should be displayed in transaction section. | All transactions are displayed in transaction section. | Firefox/ Chrome | Pass
|  | Step 2 | Go to billing section and verify transactions section.
GD_MyListings_EditListing_110 | Edit listing and then update listing from My Listing section. | Step 1 | Login and go to My listings section. | Listing should be updated successfully. | Listing is updated successfully. | Firefox/ Chrome | Pass
|  | Step 2 | Edit any listing .
|  | Step 3 | Update any filed and click on update listing.
GD_ContactUs_111 | Go to Contact link in footer and submit request. | Step 1 | Click on contact link in footer. | Contact request should be submitted successfully. | Contact request is submitted successfully. | Firefox/ Chrome | Pass
|  | Step 2 | Fill required fields and click on submit button.
GD_Verify_All links_inFooter_112 | Go to home page and verify the links in footer. | Step 1 | Click on all links in footer . | All links in the footer should be opened and displayed succsessfully. | All links in the footer are opened and displayed succsessfully. | Firefox/ Chrome | Pass
GD_ListYourHome_113 | Provide url of any video other than you tube and vimeo and verify videos section. | Step 1 | Login and go to list your home. | Video section should not updated in listing. | Video section is not updated in listing. | Firefox/ Chrome | Pass
|  | Step 2 | Provide url of a video other than you tube and vimeo. | Video should not be displayed in listing. | Video should is not displayed in listing. | Firefox/ Chrome | Pass
|  | Step 3 | Click on update listing and verify the video section.
GD_Search_InvalidValue_GuestField_114 | Search result after we provide character value in Guest field. | Step 1 | Go to home page and click to search listing after providing CheckIn,CheckOut Date and character value in guests field. | Validation message should be displayed for guest field and search result should not be displayed. | Search Result is displayed for this search. | Firefox/ Chrome | Fail | #75
GD_SearchResult_ListPhotoMapOptionView_115 | Verify the search result view of list,photo and map. | Step 1 | Search any listing. | Search result should be displayed as per selection(List,Photo,Map) | Search result is displayed as per selection(List,Photo,Map) | Firefox/ Chrome | Pass
|  | Step 2 | Click on list,photo and map and then verify the view of search result.
GD_ContactUs_BlankSubmit_116 | Verify the validation message in contact us form. | Step 1 | Submit contact us form without filling mandatory values. | Validation message should be displayed for all mandatory fields. | Validation message is displayed for all mandatory fields. | Firefox/ Chrome | Pass
GD_ForgotPassword_117 | Verify the forgot password functionality. | Step 1 | Click on forgot password link. | Email should be received with password details | Email is received with change password link. | Firefox/ Chrome | Pass
|  | Step 2 | Provide email id and click on "Reset My Password"
GD_ChangePassword_118 | Change password functionality | Step 1 | Click on Change Password hyperlink in forgot password mail. | Password should get changed and user should be able to login with new password. | User is not able to change password. | Firefox/ Chrome | Fail | #76
|  | Step 2 | Provide old and new password.
GD_ChangePassword_BlankSubmit_119 | Change password functionality with blank submit. | Step 1 | Click on Change Password hyperlink in forgot password mail. | Validation message should get displayed. | Validation message gets displayed but position of labels is changed not and error message is overlapping. | Firefox/ Chrome | Fail | #76
|  | Step 2 | Click on Change Password hyperlink without filling old and new password.
GD_SignUp_Login_Link_ForgotPassword_120 | Verify if SignUp and Login links are working correctly on Forgot password page. | Step 1 | Click on forgot password link. | Sign up and login links should be working as expected. | Sign up and login links work as expected. | Firefox/ Chrome | Pass
|  | Step 2 | Verify the SignUp and Login links on Forgot Password page.
GD_SignUp_SignIn_Link_ChangePassword_121 | Verify if SignUp and Login links are working correctly on Change password page. | Step 1 | Click onchange password link. | Sign up and SignIn links should be working as expected. | Sign up and SignIn links work as expected. | Firefox/ Chrome | Pass
|  | Step 2 | Verify the SignUp and Login links on Change Password page.
GD_List Your Home_SpecialRate _UnavailableDates_Overlapping_122 | Verify the validation message in case of specialRate_Unavailable Date overlapping. | Step 1 | Provide Special Rate date and unavailable date as overlapping. | Unavailable date should overlap the special rate date. | Unavailable date overlaps the special rate date. | Firefox/ Chrome | Pass
GD_EditPayoutMethod_blankPayPal_Email_123 | Edit Payout method with blank paypal email. | Step 1 | Edit Payout method with blank paypal email. | Validation message should be displayed | Validation message is displayed | Firefox/ Chrome | Pass
GD_Verify_the Updation_of_Bookings_In_Dashboard_124 | Verify the updation of bookings in dashboard. | Step 1 | Login and verify the updation of bookings in dashboard | Bookings,listings and Stays should be updated in dashboard. | Bookings,listings and Stays are updated in dashboard. | Firefox/ Chrome | Pass
GD_SearchResult_Sorting_Based_on_Price_125 | Search result sorting for Best Match/Highest and Lowest Price | Step 1 | Select the Best Match,Highest and Lowest price from dropdown and verify the search result. | Search result should be displayed as per selection. | Search result is not displayed as per selection. | Firefox/ Chrome | Fail | #77
GD_CreatePayoutMethod_126 | Create Payout method in Billing section. | Step 1 | Login and click on + sign for payout method and save it. | Payout method should be saved successfully. | Payout method is saved successfully. | Firefox/ Chrome | Pass
GD_CreateFavorite_LargeListName_127 | Create Favorite list and provide large list name. | Step 1 | Go to Favorite section and create list with large list name. | List name should be displayed properly. | List name is displayed properly. | Firefox/ Chrome | Pass
GD_GotoList_Link_afterCreateFavorite_128 | Hyperlink for go to lists is redirected to favorite list. | Step 1 | Click on go to list hyperlist after favorite is created. | Hyperlink for go to lists should be redirected to favorite list. | Hyperlink for go to lists is redirected to favorite list. | Firefox/ Chrome | Pass
GD_Dashboard_Edit Profile_ListYourHome_Hyperlink_Redirected_to_Correctpage_129 | Edit Profile and List your home hyperlink in DashBoard should be redirected to correct page | Step 1 | Click on Edit Profile and then List Your Home hyperlink in Dashboard page. | Edit Profile and List your home hyperlink in DashBoard should be redirected to correct page | Edit Profile and List your home hyperlink in DashBoard is redirected to correct page | Firefox/ Chrome | Pass
GD_EditTimeZone_VerifyIfdisplayed_InListing_130 | Verify the time zone in listing after updated in Booking section. | Step 1 | Verify the time zone in listing after updated in Booking section. | Time zone should be updated as selected in bookng section of listing. | Time zone is updated as selected in bookng section of listing. | Firefox/ Chrome | Pass
GD_Book same listing twice on the same date_131 | Book same listing twice on the same date. | Step 1 | Login and book a listing on the same date twice. | Validation message should be displayed. | Validation message is displayed. | Firefox/ Chrome | Pass
GD_Verify the pending bookings after time to respond is over_132 | Verify the pending bookings after time to respond is over. | Step 1 | Verify the pending bookings after time to respond is over. | Order should be closed. | Error is displayed after the time to responsd the offer is over and we click on pending booking. | Firefox/ Chrome | Fail
GD_EditProfile_AddPhoto_133 | Add photo in edit profile. | Step 1 | Add photo in edit profile. | Photo should be added and displayed successfully. | Photo is added and displayed successfully. | Firefox/ Chrome | Pass
GD_EditProfile_ChangePhoto_133 | Edit profile and change photo. | Step 1 | Edit profile and change photo and click on update photo. | Photo should be changed after we click on update photo. | Photo is changed after we click on update photo. | Firefox/ Chrome | Pass
GD_Search_134 | To check the functionality of "check in check out" option | Step 1 | Pre-requisite: User is already logged in and there exists some homes in the application in seattle | An error message should appear to let the user know that the selected dates are not valid as check out can never happen before check in | Application does not provide any error message regarding this. | Chrome | Fail | #60
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the R.H.S select check in and check out dates as 4/18/2013 and 4/10/2013 respectively
GD_Search_135 | To check the functionality of "rate per night" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home for a particular price | All the listed homes which comes under the selected price range should get displayed | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the R.H.S select rate per night scroll and listed say 125
GD_Search_136 | To check the functionality of "Type" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home for a particular type (say Room/Home) | All the listed home for type as "Room " should get displayed | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the R.H.S select "Type" as "Room"
GD_Search_137 | To check the functionality of "Min Bed" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home for 1 bed | All the listed home for which "Min Bed" is 1.5 should get displayed | Application shows the listed home for the bed less than the selected one as in this example user is able to see the listed home for 1 bed instead of his/her selection 1.5 as minimum | Chrome | Fail | #61
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the R.H.S select "Min Bed" as 1.5
GD_List_Home_138 | To check the functionality of "Feature Listing" option | Step 1 | Pre-requisite: User is already logged | Application should either accept the data or throw an error message if found invalid data | Application does not provide any error message regarding this and redirects the user to the home page | Chrome | Fail | #62
|  | Step 2 | Click on "List your home" link
|  | Step 3 | Enter all the mandatory fields and move to "feature Listing" tab
|  | Step 4 | Click on "Add" button
|  | Step 5 | Enter number as , expiration date as , security code as , postal code as
|  | Step 6 | Click on "Create payment method"
GD_List_Home_139 | Upload images | Step 1 | Pre-requisite: User is already logged | Images should get uploaded | Application gives an error message: Image could not be uploaded | Chrome | Fail | #63
|  | Step 2 | Click on "List your home" link
|  | Step 3 | Enter all the mandatory fields and move to "photos and videos " tab
|  | Step 4 | Select and try to upload any image
GD_Search_140 | To check the functionality of "Min Bath" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home for 1 bath | All the listed home for which "Min Bath" is 1.5 should get displayed | Application shows the listed home for the bath less than the selected one as in this example user is able to see the listed home for 1 bath instead of his/her selection 1.5 as minimum | Chrome | Fail | #64
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the R.H.S write 1.5 in "Min Bath" option
GD_Search_141 | To check the functionality of "Guest" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home for 1 guest | All the listed home for which "Guest" accommodation 1.5 should get displayed | Application shows the listed home for the "Guest" less than the selected one as in this example user is able to see the listed home for 1 Guest instead of his/her selection 1.5 | Chrome | Fail | #65
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the R.H.S write 1.5 in "Guest" option
GD_Search_142 | To check the functionality of "Sorting" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home | Listed homes should get sorted as per the selection | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle) | [5 empty] | `
|  | Step 3 | From the Dropdown available in the search results select highest/lowest
GD_Search_143 | "Sorting" option visibility | Step 1 | Pre-requisite: User is already logged in and listed his/her home | Options available in the dropdown should be properly visible | Dropdown options are not properly readable | Chrome | Fail | #66
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | From the Dropdown available in the search results select highest/lowest
GD_Search_144 | To check the functionality of "Must allow offers" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home | All the listed homes which provides the facility to allow offers to its users should get displayed | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | check the check box corresponding to "Must allow offers" option
GD_Search_145 | To check the functionality of "Must allow swaps" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home | All the listed homes which provides the facility to swap home to its users should get displayed | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | check the check box corresponding to "Must allow swaps" option
GD_Search_146 | To check the functionality of "Amenities" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home | All the listed homes which provides the selected "Amenities" to its users should get displayed | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | check the check box corresponding to "Amenities" option
GD_Search_147 | To check the functionality of "List" option | Step 1 | Pre-requisite: User is already logged in and listed his/her home | All the listed homes shown as search result should get display in a list | As Expected | Chrome | Pass
|  | Step 2 | Go the home page and enter the city name to search home(say--Seattle)
|  | Step 3 | Click on the list option next to search box
GD_Search_148 | Verify the email alerts from Guest Door | Step 1 | Pre-requisite: User is already logged in and listed his/her home and a different user made an offer for a listed home | All the text should be clearly visible of received email | Text is not clearly visible | Firefox/ Chrome | Fail | #78
|  | Step 2 | Check the email of the "Host" for alerts.
GD_Search_149 | To check the functionality of "Accept/decline/couner-offer" after the given time duration expired. | Step 1 | Pre-requisite: User is already logged in and listed his/her home and a different user made an offer for a listed home | Buttons under "Accept/Decline/Counter-offer should be disabled | Buttons are enable | Firefox/ Chrome | Fail | #79
|  | Step 2 | Login as "Host/Owner" after 23 hours to accept/decline/offer counter to the "Guest"
GD_Search_150 | To verify the functionality of "Accept offer" after time duration expires. | Step 1 | Pre-requisite: User is already logged in and listed his/her home and a different user made an offer for a listed home | It should not move further and throw an error message | Control moves further and shows "Create Booking" button | Firefox/ Chrome | Fail | #80
|  | Step 2 | Login as "Host/Owner" after 23 hours to accept/decline/offer counter to the "Guest"
|  | Step 3 | Click on "Accept offer" button
|  | Step 4 | Type "test" in message
|  | Step 5 | On the next page , click on " Create booking" button